## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | This set of tests is intended to check main functionality developed
Authentication (Login / Signup) functionality. |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC1.1.0 | Login panel display | GUI | 1. Launch Home page 2. Retrieve Signup panel 3. Verify Login option is visible from Signup panel | Users can navagate to a Login from signup. | A button named Login will be visible showing the login view | Login Button is shown next to a Signup. The two form the one page. | Pass
2 | 1 | TC.002 | Login panel display | GUI | 1. Launch Home page 2. Retrieve Login panel | Company name is displayed at top centre of login panel | Company name is displayed at top centre of login panel | Company name is displayed at top centre of login panel but is mispelt | Fail | Defect No 12345 Priority-1 Severity-Major | To be assigned
3.00 and 4.00 | 1 | TC.003 | Login credetinals | GUI | 1. Create valid account pwd_Naomi12 user name_naomi.hurley@gmit.ie 2. Go to Login page 3. Enter valid user name and e-mail | Home page is displayed | Successful login | Successful login | Pass
5 | 1 | TC.004 | Login credetinals | GUI | 1. Create valid account 2. Go to Login page 3. Go to User Id field and without entring data in that field press "Enter" key. | Error message validation | Error message displayed "Please enter User ID
5 | 1 | TC.005 | Login credetinals | GUI | 1. Go to Home page 2. Go to login screen Go to login screen enter "User Id" and enter wrong password try to click on "OK" button. on. | Error message validation | Error message displayed Incorrect 'Password' entered. Please enter correct password
5 | 1 | TC.006 | Login credentials | GUI | 1. Go to Home page 2. Go to login screen enter "User Id" and winthout entering password try to click on "OK" button. | Error message validation | Error message displayed "Password field is mandatory. Please enter proper password
5 | 1 | TC.007 | Login credentials | GUI | 1. Go to Home page 2. Go to login screen and enter "User ID" and password "abc12" 3. Click OK button | Error message validation | Error message"Wrong password. Please recheck and re-enter"
6 | 1 | TC.008 | Password reset | GUI | 1. Go to Home page 2. Go to login screen 3. Reset password to "gmit2014" 4. Click OK 3. Click OK button | Reset credentials functionality | Message dispayed "New password reset successfully"
6 | 1 | TC.009 | Password reset | GUI | 1. Go to Home page 2. Go to login screen 3. Select [reset] button 3. Enter user name and change password to "gmit2014" 4. Click [OK] button | Reset credentials functionality | Successful login to application
6 | 1 | TC.010 | Password reset | GUI | 1. Go to Home page 2. Go to login screen 3. Enter user name and password "Naomi12" 4. Click OK button | Reset credentials functionality | Unsuccessful login to application Message displayed "Wrong password used, please recheck"
6.1 | 1 | TC.011 | Email confirmation | GUI | 1. Create valid account pwd_Naomi12 user name_naomi.hurley@gmit.ie 2. Go to Login page 3. Enter valid user name and e-mail | Password email | Details of new login credentals emailed to client
6.2 | 1 | TC.012 | Email confirmation | GUI | 1. Repeat steps in TC.009 | Password email | Details of amended login credentals emailed to client
6.2 | 1 | TC.013 | Email confirmation | GUI | 1. Setup email acounts for Gmail, Outlook 2. Repeat steps in TC.010 3. Open Gmail and outlook | Password email | Email notifications received in Gmail and Outlook
6.2 | 1 | TC.014 | Email confirmation | GUI | 1. Repeat steps in T.003 2. Access Gmail and Outlook using IOS devices e.g. iPhone | Password email | Email notifications received in Gmail and Outlook
7 | 1 | TC.015 | Social login Facebook | GUI | 1. Set up a Facebook account 2. Go to home page 3. Select the "Sign in with Facebook" icon 3. form of single sign-on using existing login information from a social networking service such as Facebook, Twitter or Google+ to sign into a third party website in lieu of creating a new login account | Single sign in using social networks credentials | Successful login using Facebook credentials
7 | 1 | TC.016 | Social login Twiter | GUI | 1. Set up a Facebook account 2. Go to home page 3. Select the "Sign in with Facebook" icon 3. form of single sign-on using existing login information from a social networking service such as Facebook, Twitter or Google+ to sign into a third party website in lieu of creating a new login account | Single sign in using social networks credentials | Successful login using Twiter credentials
7 | 1 | TC.017 | Social login Google+ | GUI | 1. Set up a Facebook account 2. Go to home page 3. Select the "Sign in with Facebook" icon 3. form of single sign-on using existing login information from a social networking service such as Facebook, Twitter or Google+ to sign into a third party website in lieu of creating a new login account | Single sign in using social networks credentials | Successful login using Google+ credentials

## Requirement 2 Sign Up
|  | Purpose: | This set of tests is intended to check main functionality developed
Business Requirement 2 : Sign up |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments
2.1 |  | TC2.1 | Verify Login Option | Navagate to Signup overlay. Verify Log in button is visible. | Users can navagate to a Login from signup. | A button named Login will be visible showing the login view | Login Button is shown next to a Signup. The two form the one page. | Pass
2.2 |  | TC2.2 | Verify Social Sign in Options present. | Navagate to Signup overlay. Verify 3 buttons are available for Social Sign In | Users can navagate to a Provider from signup. | Checks that Oauth providers are available instead of email | 3 Providers are available for Social Sign in | Pass
2.3 |  | TC2.3 | Username must be unique | Users are required to choose a username on signup. The service should check if this chosen username |  | Checks that provider username is unique. Ensures that no duplicate signups occur with the same handle. | Upon attempting signin system checks if the username is in use If it is prompts user | Pass
2.4 |  | TC2.4 | Email Verification | Navagate to signup overlay When making an account system should check if email is a valid email if not valid should show a message to user. |  | A valid email string is required in the ‘Email’ field. | System prompts user for a valid email | Pass
2.5 |  | TC2.5 | Password Validation | Navagate to signup Attempt to create an account. | Use a password with less than 4 characters System should |  | System prompts user for a valid credentials with mor ethan 4 Characters | Pass
2.6 |  | TC2.6 | Email Confirmation | User will be required to confirm an account upon sign up. |  | Check that user email is valid by requesting a piece of info from it | email is sent containing a code and a link to verify in case the code doesent work | Pass

## Requirement 3 Login
|  | Purpose: | This set of tests is intended to check main functionality developed
Business Requirement 3 : Login |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments
3.1 |  | TC3.1 | Verify Login Option | Navagate to Signup overlay. Verify Log in button is visible. | Users can navagate to a Login from signup. | A button named Login will be visible showing the login view | Login Button is shown next to a Signup. The two form the one page. | Pass
3.2 |  | TC3.2 | Verify Social Sign in Options present. | Navagate to Signup overlay. Verify 3 buttons are available for Social Sign In | Users can navagate to a Provider from signup. | Checks that Oauth providers are available instead of email | 3 Providers are available for Social Sign in | Pass
3.3 |  | TC3.3 | Username must be unique | Users are required to choose a username on signup. The service should check if this chosen username |  | Checks that provider username is unique. Ensures that no duplicate signups occur with the same handle. | Upon attempting signin system checks if the username is in use If it is prompts user | Pass
3.4 | 1 | TC3.4 | Social login Microsoft | GUI | 1. Set up a Microsoft account 2. Go to home page 3. Select the "Microsoft" icon 3. form of single sign-on using existing login information from a social networking service such as Microsoft Twitter or Discord to sign into a third party website in lieu of creating a new login account | Single sign in using social networks credentials | Successful login using Microsoft credentials | Pass
3.5 | 1 | TC3.5 | Social login Twiter | GUI | 1. Set up a Facebook account 2. Go to home page 3. Select the "Sign in with Facebook" icon 3. form of single sign-on using existing login information from a social networking service such as Facebook, Twitter or Google+ to sign into a third party website in lieu of creating a new login account | Single sign in using social networks credentials | Successful login using Twiter credentials | Pass
3.6 | 1 | TC3.6 | Social login Discord | GUI | 1. Set up a Discord account 2. Go to home page 3. Select the "Discord" icon 3. form of single sign-on using existing login information from a social networking service such as Facebook, Twitter or Google+ to sign into a third party website in lieu of creating a new login account | Single sign in using social networks credentials | Successful login using Discord credentials | Pass

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%